## Sheet1
S. No. | Task | Starting Date | Ending Date | Description | Responsible person | Incharge and expert
Battery Management System
1 | Understanding Hardware | 2024-02-06 | 2024-02-07 | Getting familiar with uC board and sensors | All | Deepjyoth
2 | Interfacing Sensors to hardware | 2024-02-07 | 2024-06-08 | Taking data from different sensors and formating them in structured way | Pranav & Sakshi | Deepjyoth
3 | Fine Tuning recieved Data | 2024-02-09 | 2024-02-10 | Calibrating sensors and running them for a long time | Pranav & Sakshi | Deepjyoth
4 | Understanding Communication Protocol | 2024-02-09 | 2024-02-12 | Figuring Out how data will be sent over CAN | Pranav & Sakshi | Deepjyoth
5 | Sending Data over CAN | 2024-02-11 | 2024-02-12 | Sending recieved data over CAN and ensuring it is recieved properly | Pranav & Sakshi | Deepjyoth
Speed Monitoring
1 | Getting Speed Data | 2024-02-08 | 2024-02-09 |  | Pranay | Deepjyoth
2 | Formating recieved data to sendable format | 2024-02-09 | 2024-02-10 |  | Pranay | Deepjyoth
2 | Transfering it to Bluetooth | 2024-02-10 | 2024-02-11 |  | Pranay | Deepjyoth
3 | Receiving Data on Main board | 2024-02-11 | 2024-02-12 |  | Pranay | Deepjyoth
IoT Stuff
1 | Formatting data to send to ESP32 | 2024-02-08 | 2024-02-09 |  | Deepjyoth & Pranoti | Deepjyoth
2 | Sending data to ESP32 over UART | 2024-02-09 | 2024-02-10 |  | Deepjyoth & Pranoti | Deepjyoth
3 | Receiving data on ESP32 over UART | 2024-02-10 | 2024-02-11 |  | Deepjyoth & Pranoti | Deepjyoth
4 | Setting Cloud Dashboard | 2024-02-11 | 2024-02-12 |  | Deepjyoth & Pranoti | Deepjyoth
5 | Sending Data from ESP32 to Cloud | 2024-02-12 | 2024-02-13 |  | Deepjyoth & Pranoti | Deepjyoth
Main Board
1 | Designing Tasks | 2024-02-04 | 2024-02-05 | Deciding Tasks priority and scheduling | ALL | Deepjyoth
2 | Recieving Data over CAN/Bluetooth | 2024-02-07 | 2024-02-10 |  | Pranav & Sakshi | Deepjyoth
3 | Doing calculations for BMS data and predicting Battery Percentage | 2024-02-08 | 2024-02-10 |  | Pranay | Deepjyoth
4 | Sending data to ESP32 | 2024-02-09 | 2024-02-10 |  | Deepjyoth and Pranoti | Deepjyoth
5 | RTOS implementation | 2024-02-10 | 2024-02-14 |  | All | Deepjyoth
5 | Rectifying and regression testing of system | 2024-02-13 | 2024-02-15
Documentation